## Team
Initials | First | Last | Email | GitHub Username
P | Parth | Patel | ppate50@stevens.edu | parth070191
D | Deep | Patel | dpate58@stevens.edu | dpate58
B | Binjal | Patel | bpatel83@stevens.edu | patelbj3
|  |  | GitHub Repository: | agileproject

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | check date of death | AT01, AT02 | D | Done | 150 | 80 | 190 | 50 | 2015-03-01 | 2015-02-19
1 | US02 | check email-id | AT03, AT04 | D | Done | 150 | 60 | 169 | 30 | 2015-03-01 | 2015-02-20
1 | US03 | date of birth | AT05 | P | Done | 180 | 50 | 170 | 40 | 2015-03-01 | 2015-02-20
1 | US04 | Married more than once | AT06 | P | Done | 150 | 80 | 180 | 60 | 2015-03-01 | 2015-02-21
1 | US05 | Count same gender person | AT07 | B | Done | 160 | 90 | 172 | 30 | 2015-03-01 | 2015-02-21
1 | US06 | check gender of dead | AT08 | B | Done | 180 | 80 | 171 | 40 | 2015-03-01 | 2015-02-22
7 | US07 | Divorce before marriage
8 | US08 | Check husband and wife status(dead or living)
9 | US09 | Display grandchildren and grandparents
10 | US10 | Check if marriage before birth
11 | US11 | Check divorce date
12 | US12 | Function to check date format
13 | US13 | Check children age
14 | US14 | Compare birth date and death date
15 | US15 | check if widow or not
16 | US16 | Given data is correct or not
17 | US17 | Marriage before birth
18 | US18 | Married with death person
19 | US19 | Check dead person gender
20 | US20 | Check if more than 2 children
21 | US21 | Check marriage date
22 | US22 | Children age is greater than father's age
23 | US23 | check birth surname
24 | US24 | Compare marriage date and divorce date
25 | US25 | Children age is greater than mother's age
Siblings marriage

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | check date of death | In this story we will check date of death.If date is valid it display valid date and if not valid then display not valid. | AT01, AT02 | 150 | 80
US02 | check email-id | If email address is valid than it display valid other vise it display invalid. | AT03, AT04 | 150 | 60
US03 | date of birth | It this we get the birth date of every perosn in our family. | AT05 | 180 | 50
US04 | Married more than once | If any person is married more then once it display that person name. | AT06 | 150 | 80
US05 | Count same gender person | Form whole database it count the same gender and display the toatal no of male and female. | AT07 | 160 | 90
US06 | check gender of dead | In this we will check the dead person gender. | AT08 | 180 | 80

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | check date of death | death date is 10 sep 2018 | invalid death date | Passed
AT02 | US01 | check date of death | death date is12 may 1987 | No error message | Passed
AT03 | US02 | check email-id | email address is like patelbr20gmail.com | invalid email address | Passed
AT04 | US02 | check email-id | email address is like raju2004.patel@gmail.com | No error message | Passed
AT05 | US03 | date of birth | display date of birth | display date of birth | Passed
AT06 | US04 | Married more than once | display person who married more than once | No error message | Passed
AT07 | US05 | Count same gender person | count the same gender person means count male and female | No error message | passed
AT08 | US06 | check gender of dead | The person who is dead it display her/his gender | No error message | passed

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-19 | 25 |  | 0
2015-03-01 | 19 | -6 | 285 | 150 | 114
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | check date of death | AT01, AT02 | D | Done | 150 | 80 | 190 | 50 | 2015-03-01
T01 | date is valid or not
US02 | check email-id | AT03, AT04 | D | Done | 150 | 60 | 169 | 30 | 2015-03-01
T02 | email id is valdi or not
US03 | date of birth | AT05 | P | Done | 180 | 50 | 170 | 40 | 2015-03-01
T03 | Display whole family birthdate
US04 | Married more than once | AT06 | P | Done | 150 | 80 | 180 | 60 | 2015-03-01
T04 | Display person name who married more than once
US05 | Count same gender person | AT07 | B | Done | 160 | 90 | 172 | 30 | 2015-03-01
T05 | Display Total number of male and female
US06 | check gender of dead | AT08 | B | Done | 180 | 80 | 171 | 40 | 2015-03-01
T06 | Dead perosn gender display
Review Results
Keep doing:
Meet twice a week
Text everyone when you discover a problem
Avoid:
Forgetting to commit changes to GitHub

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed