## Team
Initials | First | Last | Email | GitHub Username
P | Parth | Patel | ppate50@stevens.edu | parth070191
D | Binjal | Patel | bpatel83@stevens.edu | patelbj3
B | Deep | Patel | dpate58@stevens.edu | dpate58
|  |  | GitHub Repository: | agileproject

## Backlog
Sprint | Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Added
1 | US01 | check date of death | AT01, AT02 | D | Done | 150 | 80 | 190 | 50 | 2015-03-01 | 2015-02-19
1 | US02 | check email-id | AT03, AT04 | D | Done | 150 | 60 | 169 | 30 | 2015-03-01 | 2015-02-20
1 | US03 | date of birth | AT05 | P | Done | 180 | 50 | 170 | 40 | 2015-03-01 | 2015-02-20
1 | US04 | Married more than once | AT06 | P | Done | 150 | 80 | 180 | 60 | 2015-03-01 | 2015-02-21
1 | US05 | Count same gender person | AT07 | B | Done | 160 | 90 | 172 | 30 | 2015-03-01 | 2015-02-21
1 | US06 | check gender of dead | AT08 | B | Done | 180 | 80 | 171 | 40 | 2015-03-01 | 2015-02-22
2 | US07 | check number of female is more or male in family | AT09 | D | Done | 100 | 60 | 81 | 50 | 2015-03-15 | 2015-03-07
2 | US08 | check phone number | AT10 | D | Done | 120 | 60 | 82 | 60 | 2015-03-15 | 2015-03-07
2 | US09 | display surname | AT11 | B | Done | 150 | 60 | 60 | 40 | 2015-03-15 | 2015-03-08
2 | US10 | check above 18 years | AT12 | B | Done | 150 | 50 | 161 | 90 | 2015-03-15 | 2015-03-09
2 | US11 | check number of children | AT13 | P | Done | 160 | 60 | 84 | 50 | 2015-03-15 | 2015-03-09
2 | US12 | Check if more than 2 children | AT14 | P | Done | 130 | 60 | 100 | 60 | 2015-03-15 | 2015-03-10
3 | US13 | Display residential city of person | AT15 | D | Done | 100 | 60 | 70 | 50 | 3/29 | 2015-03-17
3 | US14 | Display residential state of person | AT16 | D | Done | 120 | 50 | 81 | 50 | 3/29 | 2015-03-17
3 | US15 | Display residential country of person | AT17 | P | Done | 120 | 60 | 89 | 40 | 3/29 | 2015-03-19
3 | US16 | Display Name and Nick name | AT18 | P | Done | 120 | 60 | 57 | 60 | 3/29 | 2015-03-20
3 | US17 | Display marriage date | AT19 | B | Done | 120 | 60 | 157 | 60 | 3/29 | 2015-03-20
3 | US18 | Display the person name and his/her occupation | AT20 | B | Done | 100 | 50 | 77 | 50 | 3/29 | 2015-03-21
19 | US19 | Compare birth date and death date
20 | US20 | Function to check date format
21 | US21 | check if widow or not
22 | US22 | Children age is greater than father's age
23 | US23 | Display grandchildren and grandparents
24 | US24 | Compare marriage date and divorce date
25 | US25 | Children age is greater than mother's age
26 | US26 | Check divorce date
27 | US27 | Divorce before marriage
28 | US28 | Check husband and wife status(dead or living)
29 | US29 | Married with death person

## Stories
Story ID | Story Name | Story Description | Acc Tests | Est Size | Est Time
US01 | check date of death | In this story we will check date of death.If date is valid it display valid date and if not valid then display not valid. | AT01, AT02 | 150 | 80
US02 | check email-id | If email address is valid than it display valid other vise it display invalid. | AT03, AT04 | 150 | 60
US03 | date of birth | It this we get the birth date of every perosn in our family. | AT05 | 180 | 50
US04 | Married more than once | If any person is married more then once it display that person name. | AT06 | 150 | 80
US05 | Count same gender person | Form whole database it count the same gender and display the toatal no of male and female. | AT07 | 160 | 90
US06 | check gender of dead | In this we will check the dead person gender. | AT08 | 180 | 80
US07 | check number of female is more or male in family | In this we get that female is more or male is more in family and display it. | AT09 | 100 | 60
US08 | check phone number | In this we get the valid phone number and display it from our family tree. | AT10 | 120 | 60
US09 | display surname | Using this user story we will get the surname of person in family. | AT11 | 150 | 60
US10 | check above 18 years | In this we get the person name who is above 18 years and display that person name. | AT12 | 150 | 50
US11 | check number of children | IN this we will get the person name who have more than 1 children and display it. | AT13 | 160 | 60
US12 | Check if more than 2 children | In this it display the person name if they have more than 2 children. | AT14 | 130 | 60
US13 | Display residential city of person | It will display the person name and display city name where they are living. | AT15 | 100 | 60
US14 | Display residential state of person | Uisng this we will display the person name and person state name and display it. | AT16 | 120 | 50
US15 | Display residential country of person | It will give the person namr and the country where he or she living and display it. | AT17 | 120 | 60
US16 | Display Name and Nick name | In this it will display the person name and display her or his nick name. | AT18 | 120 | 60
US17 | Display marriage date | It will display the couple name and also check their marriage date and display it. | AT19 | 120 | 60
US18 | Display the person name and his/her occupation | In this it will give the person name and their occupation and also diplay it. | AT20 | 100 | 50

## Tests
AT ID | Story ID | Story Name | Input | Expected Output | Status
AT01 | US01 | check date of death | death date is 10 sep 2018 | invalid death date | Passed
AT02 | US01 | check date of death | death date is12 may 1987 | No error message | Passed
AT03 | US02 | check email-id | email address is like patelbr20gmail.com | invalid email address | Passed
AT04 | US02 | check email-id | email address is like raju2004.patel@gmail.com | No error message | Passed
AT05 | US03 | date of birth | display date of birth | display date of birth | Passed
AT06 | US04 | Married more than once | display person who married more than once | No error message | Passed
AT07 | US05 | Count same gender person | count the same gender person means count male and female | No error message | passed
AT08 | US06 | check gender of dead | The person who is dead it display her/his gender | No error message | passed
AT09 | US07 | check number of female is more or male in family | female is more or male is more | male is more in family | passed
AT10 | US08 | check phone number | Display phone valid number | Display phone valid number | passed
AT11 | US09 | display surname | Display surname | No error message | passed
AT12 | US10 | check above 18 years | Display above 18 year person name | No error message | passed
AT13 | US11 | check number of children | Display person name and total number of children that person have | No error message | passed
AT14 | US12 | Check if more than 2 children | Display person name if person have more than 2 children | No error message | passed
AT15 | US13 | Display residential city of person | It display the person name and the city where he/she is living. | No error message | passed
AT16 | US14 | Display residential state of person | It display the stste and person name who live in which state | No error message | passed
AT17 | US15 | Display residential country of person | Display the country name and person name with state where he/she is living | No error message | passed
AT18 | US16 | Display Name and Nick name | Display the couple name where the both husband and wife are dead | No error message | passed
AT19 | US17 | Display marriage date | It will dislay the person name and their marriage date. | No error message | passed
AT20 | US18 | Display the person name and his/her occupation | It will display the person name and hie or her occupation. | No error message | passed

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2015-02-19 | 29 |  | 0
2015-03-01 | 23 | -6 | 285 | 150 | 114
2015-03-15 | 17 | -6 | 568 | 140 | 121.2857
2015-03-29 | 11 | -6 | 602 | 140 | 14.5714
#DIV/0!
#DIV/0!

## Sprint1
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | check date of death | AT01, AT02 | D | Done | 150 | 80 | 190 | 50 | 2015-03-01
T01 | date is valid or not
US02 | check email-id | AT03, AT04 | D | Done | 150 | 60 | 169 | 30 | 2015-03-01
T02 | email id is valdi or not
US03 | date of birth | AT05 | P | Done | 180 | 50 | 170 | 40 | 2015-03-01
T03 | Display whole family birthdate
US04 | Married more than once | AT06 | P | Done | 150 | 80 | 180 | 60 | 2015-03-01
T04 | Display person name who married more than once
US05 | Count same gender person | AT07 | B | Done | 160 | 90 | 172 | 30 | 2015-03-01
T05 | Display Total number of male and female
US06 | check gender of dead | AT08 | B | Done | 180 | 80 | 171 | 40 | 2015-03-01
T06 | Dead perosn gender display
Review Results
Keep doing:
Meet twice a week
Text everyone when you discover a problem
Avoid:
Forgetting to commit changes to GitHub

## Sprint2
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US07 | check number of female is more or male in family | AT09 | D | Done | 100 | 60 | 81 | 50 | 2015-03-15
T07 | Display who is more in family means male are more or female
US08 | check phone number | AT10 | D | Done | 120 | 60 | 82 | 60 | 2015-03-15
T08 | Display phone number
US09 | display surname | AT11 | B | Done | 150 | 60 | 60 | 40 | 2015-03-15
T09 | display whole family surname
US10 | check above 18 years | AT12 | B | Done | 150 | 50 | 161 | 90 | 2015-03-15
T10 | Display the person name who's age is above 18 year
US11 | check number of children | AT13 | P | Done | 160 | 60 | 84 | 50 | 2015-03-15
T11 | Display the couple name name and no of children they have
US12 | Check if more than 2 children | AT14 | P | Done | 130 | 60 | 100 | 60 | 2015-03-15
T12 | Display the person name who have more than 2 children.
Review Results
Keep doing:
Meeting 4 days in a week
Dividing the work to execute
Text everyone when anyone discovers a problem
Informing everyone how much work is completed and what is left
Avoid:
Forgetting to commit changes to GitHub
Miscommunication
Forget to meet others

## Sprint3
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US13 | Display residential city of person | AT15 | D | Done | 100 | 60 | 70 | 50 | 3/29
T13 | In this it display the person name and his current residential city
US14 | Display residential state of person | AT16 | D | Done | 80 | 50 | 81 | 50 | 3/29
T14 | Check the person name and display person name with current state
US15 | Display residential country of person | AT17 | B | Done | 80 | 60 | 89 | 40 | 3/29
T15 | Display person name and his country where he or she is living.
US16 | Display Name and Nick name | AT18 | B | Done | 100 | 60 | 57 | 60 | 3/29
T16 | Display the person name and hie or her nick name
US17 | Display marriage date | AT19 | P | Done | 80 | 60 | 157 | 60 | 3/29
T17 | It will display the couple name ans their marriage date
US18 | Display the person name and his/her occupation | AT20 | P | Done | 100 | 50 | 77 | 50 | 3/29
T18 | Check occupation of person and dipaly thie name and occupation
Review Results
Keep doing:
Meeting 5 days in a week
Dividing the work to execute
Informing everyone how much work is completed and what is left
Discuss all things with group member
Avoid:
Forgetting to commit changes to GitHub
Miscommunication
Forget to meet others

## Sprint4
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US19 | check if widow or not |  | D |  | 100 | 60
US20 | Compare marriage date and divorce date |  | D |  | 120 | 50
US21 | Divorce before marriage |  | B |  | 100 | 60
US22 | Check divorce date |  | B |  | 150 | 60
US23 | Married with death person |  | P |  | 140 | 50
US24 | Display grandchildren and grandparents |  | P |  | 130 | 60

## Sprint5
Story ID | Story Name | Acc Tests | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed